## Sheet1
Work | Task | Responsible Team Member | Start Date | End Date | Duration (in days)
Data Understanding | Variable datatypes study, business understanding | Lekshmi, Patricia and Pooja (Dataset has 81 column) | 16/07/2021 | 19/07/2021 | 3
Exploratory Data Analysis | Handling Missing Values | Pooja | 19/07/2021 | 21/07/2021 | 2
| Outlier Detection | Patricia | 19/07/2021 | 21/07/2021 | 2
| Descriptive Analysis | Lekshmi | 19/07/2021 | 21/07/2021 | 2
| Correlation Analysis | Pooja | 22/07/2021 | 24/07/2021 | 2
| Simple Charts and Graphs | Patricia | 22/07/2021 | 24/07/2021 | 2
| Variable Transformation | Lekshmi | 22/07/2021 | 24/07/2021 | 2
| Identify potential variables for modeling | Pooja & Patricia | 25/07/2021 | 28/07/2021 | 3
Modeling | Split data into train and test | Lekshmi | 28/07/2021 | 29/07/2021 | 1
| Multiple Linear Regression/ Random Forest | Lekshmi, Patricia and Pooja | 30/07/2021 | 2021-01-08 | 3
| Assumption Testing | Lekshmi & Patricia | 2021-02-08 | 2021-03-08 | 1
| Model Testing in test data | Pooja | 2021-03-08 | 2021-04-08 | 1
| Model Evaluation ( AUC, ROC, RMSE, MSE, Rsquare, Std Error etc) | Lekshmi & Pooja | 2021-04-08 | 2021-06-08 | 2
| Model Validation | Patricia | 2021-06-08 | 2021-06-08 | 1
Report & presentation |  | Lekshmi, Patricia and Pooja | 26/07/2021 | 2021-06-08 | 10